## Organizational Profile
Lightwell Care Group – Healthcare Risk Assessment (Simulated Data)
Prepared by: GRC Analyst, Lightwell Care Group ¦ Version 1.0 ¦ Reporting date 16 Oct 2026 ¦ ALL DATA IS FICTIONAL
START HERE: Read the methodology and executive summary (PDF) first, then Risk Register, Risk Matrix, Treatment, Owner Report.
Item | Detail
Organisation | Lightwell Care Group – Lightwell Medical Centre (fictional), single site
Location (fictional) | Merseyside, England; urban practice, high deprivation index
Registered patients | 18640
Headcount | 74 staff (58.6 WTE): 11 GPs (8.4 WTE), 5 nurses/ANPs, 3 HCAs, 2 clinical pharmacists, 24 admin/reception, 6 management, 23 other
Services | General practice, minor surgery, vaccinations, diagnostics (phlebotomy, ECG, X-ray referrals), in-house pharmacy support, urgent same-day clinic
Annual income (simulated) | £6.4m (NHS contract £5.6m; private and other £0.8m)
Clinical systems | Supplier-hosted EPR; on-site server room; NHSmail; online consultation tool; AI scribe pilot (paused)
Regulatory context | CQC registered (last rating: Good, March 2023 – fictional); UK GDPR / DPA 2018; DSPT (2 evidence items outstanding); DCB0129/0160
Risk appetite statement | Low appetite for patient safety, safeguarding and regulatory risk; moderate for financial and operational risk. Residual scores above the appetite threshold on the Criteria sheet must have a treatment plan.
Methodology | 5x5 likelihood x impact; inherent (before controls) and residual (after existing controls); treatment plan targets residual within appetite. Aligned to ISO 31000 / ISO 27005 concepts.
Assumptions | All people, figures and incidents are simulated for training/portfolio purposes. Regulatory references are real. Costs are indicative estimates.
Workbook guide
Sheet | Purpose
Criteria | Likelihood/impact scales, rating bands, appetite threshold and reporting date (inputs: change here and everything recalculates)
Risk Register | 31 risks with inherent and residual scoring, controls, owners, appetite status, next review date
Risk Matrix | Inherent and residual 5x5 heat maps (counts) and residual risk IDs per cell
Treatment | Risk treatment plan with owners, dates, cost, target residual score and RAG
Owner Report | Headline metrics, per-owner report and category summary for the Risk Committee
KRI Data | Simulated 12-month key risk indicators supporting likelihood scoring
Owners | Risk owner directory

## Criteria
Scoring Criteria and Risk Appetite
Report date | 2026-10-16
Likelihood scale
Score | Level | Description | Indicative Frequency
1 | Rare | Highy unlikely, no harm | Less than once in 10 years
2 | Unlikely | Could occur but not expected | Once in 5 - 10 years
3 | Possible | Might occur at some time | Once in 1 - 5 years
4 | Likely | Will probably occur | Once in a year
5 | Almost certain | Expected to occur, possibly repeatedly | Monthly or more often
Impact scale
Score | Level | Patient safety | Data protection | Financial | Operational | Regulatory/Reputation
1 | Negligible | No harm | Minor, no personal data exposed | < £5k | < 1 hour disruption | No external interest
2 | Minor | Minor harm, minor reversible disruption | Internal breach, few records, contained | £5k - £25k | Up to half a day; workaround available | Informal feedback; complaint
3 | Moderate | Service delay, short-term harm needing treatment | Reportable to DPO; limited records | £25k - £100k | 1-3 days; service reduced | Formal complaint; CQC query
4 | Major | Serious or long-term harm, major service failure | ICO - reportable; large volume or special category data | £100k - £500k | 3 - 7 days; service suspended | CQC warning notice; ICO investigate; local media
5 | Severe | Prolong critical service failure, Dealth or multiple serious harm | Mass breach, sustained loss of clinical data | > £500k | > 7 days; closure or loss of contract | Enforcement/prosecution; national media; registration at risk.
Rating bands
Rating | Min score | Max score | Review frequency (days) | Required response | Escalation
Low | 1 | 4 | 180 | Accept and monitor | Risk owner
Medium | 5 | 9 | 90 | Manage within normal controls | Department Lead
High | 10 | 15 | 60 | Treatment plan required; senior oversight | Risk Committee
Critical | 16 | 25 | 30 | Immediate action; executive attention | Board / Partners
Risk appetite: maximum acceptable residual score | 9 | Assumption: residual scores above this value are outside appetite and need treatment
Risk appetite by category (maximum acceptable residual score)
Category | Max residual score | Appetite statement
Clinical Safety | 6 | Averse: patient safety is the first priority; tolerate only low-moderate residual risk.
Medicines Management | 6 | Averse: zero tolerance for avoidable medicines harm.
Information Security | 8 | Cautious: accept medium residual risk only where controls are monitored.
Data Protection | 8 | Cautious: personal data breaches must be minimised and reported on time.
Regulatory & Compliance | 8 | Cautious: aim for no enforcement action or adverse CQC rating.
Operational Resilience | 9 | Moderate: some service disruption acceptable if patient safety is protected.
Workforce | 9 | Moderate: accept market-driven pressures with active mitigation.
Facilities & H & S | 8 | Cautious: statutory safety duties must be met.
Financial | 9 | Moderate: accept budget volatility within agreed reserves.
Third-Party | 8 | Cautious: critical suppliers need ongoing assurance.
Treatment options
Option | Meaning
Mitigate | Reduce likelihood or impact through new or improved controls.
Transfer | Share the risk, for example through insurance or contract terms
Avoid | Stop the activity that creates the risk
Accept | Tolerate the residual risk with monitoring; must be within appetite or formally approved

## Risk Register
Risk Register – Lightwell Medical Centre
Inherent = before controls; Residual = after existing controls. Scores and ratings are formulas driven by the Criteria sheet.
ID | Category | Risk title | Risk description (cause, event, consequence) | Assets affected | Risk owner (role) | Inherent likelihood | Inherent impact | Inherent score | Inherent rating | Existing controls | Control effectiveness | Residual likelihood | Residual impact | Residual score | Residual rating | Appetite status | Treatment option | Regulation / framework | Date identified | Last reviewed | Next review due | Status
R01 | Cyber Security | Ransomware attack on clinical systems | There is a risk that phishing or exploitation of an unpatched vulnerability enables ransomware to compromise the electronic patient record and file servers, resulting in interrupted consultations, loss of access to clinical records, potential exposure of patient information and financial loss. | EPR, file servers, backups and patient information | Head of IT & Digital | 4 | 5 | 20 | Critical | Endpoint detection (EDR); daily backups; email filtering; quarterly restore tests (2 of last 4 passed) | Partially effective - recovery reliability is not adequately demonstrated; phishing awareness and patching effectiveness require assessment. | 3 | 4 | 12 | High | Outside appetite | Mitigate + Transfer | NCSC guidance; DSPT; Cyber Essentials Plus; UK GDPR Art.32 | 2026-09-14 | 2026-10-19 | 2026-12-18 | Open – treatment in progress
R02 | Cyber Security | Compromise of staff credentials via phishing | Staff account takeover gives attacker access to email and clinical records; MFA not yet on all systems. | Staff accounts, NHSmail, EPR | Head of IT & Digital | 5 | 4 | 20 | Critical | MFA on email only; annual phishing awareness training; password policy | Weak | 4 | 3 | 12 | High | Outside appetite | Mitigate | DSPT; Cyber Essentials; UK GDPR Art.32 | 2026-09-15 | 2026-10-19 | 2026-12-18 | Open – treatment in progress
R03 | Cyber Security | Unsupported legacy systems (imaging workstations) | Four diagnostic imaging workstations run an unsupported operating system and cannot be patched, creating an exploitable entry point. | Imaging workstations, PACS link | Head of IT & Digital | 4 | 4 | 16 | Critical | Partial network segmentation; vendor remote access disabled by default | Weak | 3 | 4 | 12 | High | Outside appetite | Mitigate | Cyber Essentials Plus; DSPT; MHRA medical device guidance | 2026-09-16 | 2026-10-19 | 2026-12-18 | Open – treatment in progress
R04 | Data Protection | Inappropriate access to patient records by staff | Staff view records without a legitimate relationship (e.g. colleagues, family, public figures), causing a UK GDPR breach and loss of trust. | EPR, patient records | Data Protection Officer | 4 | 4 | 16 | Critical | Role-based access; access audit logs exist but reviewed ad hoc; confidentiality agreements | Weak | 3 | 3 | 9 | Medium | Within appetite | Mitigate | UK GDPR Art.5(1)(f); Caldicott Principles; DSPT | 2026-09-17 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R05 | Data Protection | Misdirected email or letter containing patient data | Human error sends clinical correspondence to the wrong recipient, leading to a reportable incident. | Correspondence, referral letters | Data Protection Officer | 5 | 3 | 15 | High | NHSmail encryption; pre-send checklist; incident reporting culture | Adequate | 4 | 2 | 8 | Medium | Within appetite | Mitigate | UK GDPR Art.33; ICO breach guidance | 2026-09-18 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R06 | Data Protection | Subject Access Requests (SARs) not met within one month | Rising SAR volumes and manual redaction cause missed statutory deadlines, ICO complaints and possible enforcement. | SAR process, records team | Data Protection Officer | 4 | 3 | 12 | High | SAR tracker; templates; two trained administrators; DPO oversight | Adequate | 3 | 2 | 6 | Medium | Within appetite | Accept | UK GDPR Art.12 & 15; Data Protection Act 2018 | 2026-09-19 | 2026-10-19 | 2027-01-17 | Open – monitoring
R07 | Data Protection | AI scribe / cloud processor deployed without DPIA or DPA | A new AI documentation tool processes consultation audio before a DPIA, data processing agreement and clinical safety case are in place. | AI scribe pilot, consultation data | Data Protection Officer | 3 | 4 | 12 | High | Procurement checklist (not consistently applied); pilot paused pending review | Weak | 2 | 4 | 8 | Medium | Within appetite | Avoid | UK GDPR Art.28 & 35; DCB0160; ICO AI guidance | 2026-09-20 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R08 | Information Security | Loss or theft of portable device | Laptop or tablet used on home visits is lost or stolen, exposing cached patient data. | Laptops, tablets (home visits) | Head of IT & Digital | 3 | 4 | 12 | High | Full-disk encryption on 85% of devices; remote wipe; asset register | Adequate | 2 | 3 | 6 | Medium | Within appetite | Mitigate | UK GDPR Art.32; DSPT | 2026-09-21 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R09 | Operational Resilience | Prolonged EPR outage (>4 hours) | Supplier-hosted EPR is unavailable, forcing paper downtime working and delaying care. | Hosted EPR, network | Head of IT & Digital | 3 | 4 | 12 | High | Supplier SLA 99.5%; paper downtime procedure; read-only offline view | Adequate | 2 | 4 | 8 | Medium | Within appetite | Mitigate | DSPT; NHS EPRR core standards | 2026-09-22 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R10 | Business Continuity | Loss of power or server room failure | On-site server room has limited UPS capacity (about 20 minutes) and no generator connection, risking data loss and extended closure. | Server room, building power | Estates & Facilities Manager | 3 | 4 | 12 | High | UPS 20 min; quarterly UPS test; BC plan references manual workarounds | Weak | 2 | 4 | 8 | Medium | Within appetite | Mitigate | ISO 22301; NHS EPRR core standards | 2026-09-23 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R11 | Business Continuity | Outbreak or pandemic causing >20% staff absence | Seasonal infection waves reduce clinical capacity and strain safe staffing. | Workforce, clinic capacity | Practice Manager | 3 | 4 | 12 | High | BC plan; flexible rota; bank staff list; vaccination programme | Adequate | 3 | 3 | 9 | Medium | Within appetite | Mitigate | NHS EPRR core standards; HSE | 2026-09-24 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R12 | Clinical Safety | Delayed review of test results leading to missed diagnosis | Abnormal pathology or imaging results are not actioned in time, delaying treatment of serious conditions. | Results workflow, clinicians | Clinical Director | 3 | 5 | 15 | High | Result-tracking workflow; weekly inbox audit; buddy system for leave | Adequate | 2 | 5 | 10 | High | Outside appetite | Mitigate | CQC Reg.12; GMC Good Medical Practice | 2026-09-25 | 2026-10-19 | 2026-12-18 | Open – treatment in progress
R13 | Clinical Safety | Medication prescribing error | Wrong drug, dose or interaction prescribed, causing patient harm. | Prescribing, EPR decision support | Clinical Director | 4 | 4 | 16 | Critical | Decision-support alerts; pharmacist review of repeat prescribing; incident learning | Adequate | 3 | 3 | 9 | Medium | Within appetite | Mitigate | CQC Reg.12; NICE medicines optimisation | 2026-09-14 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R14 | Medicines Management | Controlled drugs discrepancies or non-compliant storage | CD register errors or storage failures lead to loss, diversion or regulatory action. | CD cupboard, register | Pharmacy Lead | 3 | 4 | 12 | High | CD register; monthly stock check; dual signature; locked cabinet to standard | Adequate | 2 | 3 | 6 | Medium | Within appetite | Accept | Misuse of Drugs Regulations 2001; CQC Reg.12 | 2026-09-15 | 2026-10-19 | 2027-01-17 | Open – monitoring
R15 | Medicines Management | Vaccine cold-chain failure | Fridge temperature excursion spoils stock and patients receive compromised vaccines or lose appointments. | Vaccine fridges | Pharmacy Lead | 3 | 3 | 9 | Medium | Calibrated data loggers; alarms; daily checks; three excursions in last 12 months | Adequate | 2 | 3 | 6 | Medium | Within appetite | Accept | Green Book; UKHSA cold chain guidance | 2026-09-16 | 2026-10-19 | 2027-01-17 | Open – monitoring
R16 | Clinical Safety | Failure to recognise deteriorating patient or sepsis at triage | Non-clinical or junior staff do not escalate red-flag symptoms in time, causing serious harm. | Reception triage, nurse triage | Head of Nursing | 3 | 5 | 15 | High | Red-flag triage protocol; annual training; GP-on-call escalation route | Adequate | 2 | 5 | 10 | High | Outside appetite | Mitigate | CQC Reg.12; NICE NG51 sepsis | 2026-09-17 | 2026-10-19 | 2026-12-18 | Open – treatment in progress
R17 | Infection Prevention | Healthcare-associated infection after minor surgery | Inadequate decontamination or aseptic technique leads to a surgical site infection cluster. | Treatment room, instruments | IPC Lead | 3 | 4 | 12 | High | Single-use instruments; outsourced sterile services; twice-yearly IPC audit | Strong | 2 | 3 | 6 | Medium | Within appetite | Accept | Health and Social Care Act Code of Practice on IPC; CQC Reg.12 | 2026-09-18 | 2026-10-19 | 2027-01-17 | Open – monitoring
R18 | Safeguarding | Missed or late safeguarding referral | Concerns for a child or vulnerable adult are not identified or escalated, resulting in harm. | Clinical staff, safeguarding register | Safeguarding Lead | 3 | 5 | 15 | High | Named lead; Level 3 training (84% compliant); multi-agency meetings | Adequate | 2 | 5 | 10 | High | Outside appetite | Mitigate | Children Act 1989/2004; Care Act 2014; CQC Reg.13 | 2026-09-19 | 2026-10-19 | 2026-12-18 | Open – treatment in progress
R19 | Workforce | Clinical vacancies and burnout causing unsafe staffing | GP and nurse vacancies, high locum use and burnout reduce continuity and increase error risk. | Clinical workforce | HR Manager | 5 | 4 | 20 | Critical | Locum framework; retention initiatives; rota review (vacancy rate 17%) | Weak | 4 | 3 | 12 | High | Outside appetite | Mitigate | CQC Reg.18; NHS People Plan | 2026-09-20 | 2026-10-19 | 2026-12-18 | Open – treatment in progress
R20 | Workforce | Mandatory training non-compliance | Overdue statutory training (fire, IPC, safeguarding, IG) exposes the organisation to regulatory criticism and unsafe practice. | Training records (LMS) | HR Manager | 4 | 3 | 12 | High | LMS with email reminders; monthly compliance report | Adequate | 3 | 2 | 6 | Medium | Within appetite | Mitigate | CQC Reg.18; DSPT Standard 3 | 2026-09-21 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R21 | Workforce | Dependence on key individuals (single points of failure) | Loss of the practice manager or IT lead with undocumented knowledge disrupts operations. | Key roles, procedures | Practice Manager | 3 | 3 | 9 | Medium | Partial procedure documentation; informal deputising | Weak | 3 | 3 | 9 | Medium | Within appetite | Mitigate | ISO 22301; good governance practice | 2026-09-22 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R22 | Regulatory Compliance | Adverse CQC inspection outcome or rating downgrade | Governance gaps (audit, incident learning, policy control) lead to enforcement action or a lower rating. | Governance framework | Quality & Compliance Lead | 3 | 4 | 12 | High | Annual internal audit plan; policy review cycle; incident learning meetings | Adequate | 2 | 4 | 8 | Medium | Within appetite | Mitigate | CQC Reg.17 (good governance) | 2026-09-23 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R23 | Regulatory Compliance | Digital clinical safety and DSPT non-compliance | New digital tools go live without a Clinical Safety Officer sign-off; two DSPT evidence items remain outstanding. | Digital tools, DSPT submission | Quality & Compliance Lead | 3 | 4 | 12 | High | DSPT working group; ad hoc safety review | Weak | 3 | 3 | 9 | Medium | Within appetite | Mitigate | DCB0160; DSPT; DTAC | 2026-09-24 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R24 | Financial | Funding shortfall and cost inflation | Flat contract funding against rising staffing, drug and energy costs creates an operating deficit. | Budget, ICB contract | Finance Director | 4 | 4 | 16 | Critical | Monthly management accounts; reserves policy; quarterly forecast | Adequate | 3 | 3 | 9 | Medium | Within appetite | Accept | Partnership agreement; NHS contract | 2026-09-25 | 2026-10-19 | 2027-01-17 | Open – monitoring
R25 | Financial | Payroll or invoice fraud | Fake supplier invoice or payroll diversion leads to financial loss. | Finance system, bank mandates | Finance Director | 2 | 4 | 8 | Medium | Dual authorisation; supplier bank-detail call-back; segregation of duties | Strong | 1 | 4 | 4 | Low | Within appetite | Accept | Fraud Act 2006; internal financial controls | 2026-09-14 | 2026-10-19 | 2027-04-17 | Open – monitoring
R26 | Supply Chain | Failure of critical supplier (pathology or clinical waste) | Pathology provider or waste contractor fails, delaying diagnostics or breaching waste regulations. | Pathology, clinical waste contracts | Chief Executive | 3 | 4 | 12 | High | Contracts with SLAs; alternative waste carrier on call; no secondary pathology supplier | Weak | 3 | 3 | 9 | Medium | Within appetite | Mitigate | Health and Safety at Work Act; HTM 07-01 | 2026-09-15 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R27 | Estates & H&S | Fire safety non-compliance | Fire doors, alarms or evacuation drills fall short of standard, risking injury and enforcement action. | Premises, fire systems | Estates & Facilities Manager | 3 | 5 | 15 | High | Fire risk assessment; weekly alarm tests; 2 of 4 planned drills completed | Adequate | 2 | 5 | 10 | High | Outside appetite | Mitigate | Regulatory Reform (Fire Safety) Order 2005 | 2026-09-16 | 2026-10-19 | 2026-12-18 | Open – treatment in progress
R28 | Estates & H&S | Legionella in water systems | Stagnant or poorly maintained water systems cause Legionella growth and patient or staff infection. | Water systems | Estates & Facilities Manager | 2 | 5 | 10 | High | Annual risk assessment; quarterly sampling; temperature monitoring; flushing log | Adequate | 1 | 5 | 5 | Medium | Within appetite | Accept | HSE ACOP L8; HSG274 | 2026-09-17 | 2026-10-19 | 2027-01-17 | Open – monitoring
R29 | Estates & H&S | Violence and aggression towards staff | Abusive patients and relatives cause injury, stress and staff turnover (41 incidents in 12 months). | Reception, clinical rooms | Practice Manager | 5 | 3 | 15 | High | Zero-tolerance policy; panic alarms; warning letters; incident reporting | Adequate | 4 | 2 | 8 | Medium | Within appetite | Mitigate | Health and Safety at Work Act; NHS Violence Reduction Standard | 2026-09-18 | 2026-10-19 | 2027-01-17 | Open – treatment in progress
R30 | Reputation | Reputational damage from breach or complaints publicity | A serious incident or viral complaint erodes patient trust and registrations. | Brand, patient list | Chief Executive | 3 | 3 | 9 | Medium | Communications plan; complaints procedure; patient participation group | Adequate | 2 | 3 | 6 | Medium | Within appetite | Accept | CQC Reg.16; ICO transparency | 2026-09-19 | 2026-10-19 | 2027-01-17 | Open – monitoring
R31 | Operational Resilience | Poor access: long waits and high DNA rates | Appointment demand outstrips capacity, causing complaints, harm from delays and lower patient satisfaction. | Appointment system | Practice Manager | 5 | 3 | 15 | High | Triage and sit-and-wait slots; text reminders; extended hours (DNA rate 9.4%) | Adequate | 4 | 3 | 12 | High | Outside appetite | Mitigate | CQC Reg.9; GP contract access requirements | 2026-09-20 | 2026-10-19 | 2026-12-18 | Open – treatment in progress
Note: blue = scorer inputs (1–5). Likelihood/impact values are analyst judgements informed by the KRI Data sheet.

## Treatment
Risk Treatment Plan
Targets are expected residual scores once the action is complete. RAG is calculated against the reporting date on the Criteria sheet.
Action ID | Risk ID | Risk title | Current residual score | Treatment option | Treatment action | Risk owner (role) | Action lead | Start date | Target date | Est. cost (£) | Status | % complete | Target likelihood | Target impact | Target score | Expected reduction | Target rating | RAG | Success measure
A01 | R01 | Ransomware attack on clinical systems | 12 | Mitigate | Implement immutable off-site backups and quarterly full restore tests. Deliver role-based phishing awareness training. Review and strengthen email filtering and implement MFA for email. Implement a monitored patching schedule. Agree alternative protections where clinical or supplier constraints prevent patching. | Head of IT & Digital | Network & Systems Manager | 2026-09-28 | 2026-12-18 | 14500 | In progress | 40% | 2 | 3 | 6 | 6 | Medium | On track | 4/4 quarterly restore tests passed; RPO ≤ 24h
A02 | R01 | Ransomware attack on clinical systems | 12 | Transfer | Renew cyber and business-interruption insurance with ransomware cover | Head of IT & Digital | Finance Director (broker liaison) | 2026-10-01 | 2026-11-30 | 18000 | In progress | 50% | 2 | 3 | 6 | 6 | Medium | On track | Policy in force with ≥ £1m cyber limit
A03 | R02 | Compromise of staff credentials via phishing | 12 | Mitigate | Extend MFA to EPR, VPN and all admin accounts; run quarterly phishing simulations | Head of IT & Digital | Network & Systems Manager | 2026-09-21 | 2026-11-30 | 6200 | In progress | 60% | 2 | 3 | 6 | 6 | Medium | On track | 100% MFA coverage; phishing click rate ≤ 5%
A04 | R03 | Unsupported legacy systems (imaging workstations) | 12 | Mitigate | Replace or isolate unsupported imaging workstations on a segregated VLAN | Head of IT & Digital | Network & Systems Manager | 2026-10-05 | 2027-02-26 | 38000 | Not started | 0% | 2 | 4 | 8 | 4 | Medium | Late start | 0 systems on unsupported OS
A05 | R04 | Inappropriate access to patient records by staff | 9 | Mitigate | Monthly audit-log review with automated alerts for own-record, colleague and VIP access | Data Protection Officer | DPO / IT Analyst | 2026-10-01 | 2026-12-18 | 7500 | In progress | 10% | 2 | 3 | 6 | 3 | Medium | On track | 100% of monthly reviews completed; all alerts triaged in 5 days
A06 | R05 | Misdirected email or letter containing patient data | 8 | Mitigate | Introduce recipient-verification prompt in EPR letters and DLP on NHSmail | Data Protection Officer | DPO / IT Analyst | 2026-10-12 | 2026-12-04 | 1800 | In progress | 20% | 3 | 2 | 6 | 2 | Medium | On track | Misdirected incidents reduced by 50%
A07 | R07 | AI scribe / cloud processor deployed without DPIA or DPA | 8 | Avoid | Pause AI scribe go-live until DPIA, DPA, DCB0160 safety case and supplier assurance are complete | Data Protection Officer | DPO / Clinical Safety Officer | 2026-09-16 | 2026-11-06 | 2000 | In progress | 65% | 1 | 4 | 4 | 4 | Low | On track | Signed DPIA and DPA before any live use
A08 | R08 | Loss or theft of portable device | 6 | Mitigate | Complete encryption rollout to remaining 15% of portable devices | Head of IT & Digital | IT Support Lead | 2026-09-28 | 2026-11-06 | 2400 | In progress | 80% | 1 | 3 | 3 | 3 | Low | On track | 100% devices encrypted on asset register
A09 | R09 | Prolonged EPR outage (>4 hours) | 8 | Mitigate | Implement hot-standby network failover and run twice-yearly downtime drills | Head of IT & Digital | Network & Systems Manager | 2026-11-02 | 2027-03-12 | 28000 | Not started | 0% | 2 | 3 | 6 | 2 | Medium | On track | Unplanned downtime ≤ 4h/yr; drills completed
A10 | R10 | Loss of power or server room failure | 8 | Mitigate | Extend UPS to 4 hours and install generator connection point | Estates & Facilities Manager | Estates Officer | 2026-11-16 | 2027-02-12 | 31000 | Not started | 0% | 1 | 4 | 4 | 4 | Low | On track | Server room survives 4h outage test
A11 | R11 | Outbreak or pandemic causing >20% staff absence | 9 | Mitigate | Annual BC exercise and surge-staffing plan with bank staff agreements | Practice Manager | Practice Manager | 2026-10-19 | 2027-01-29 | 3000 | Not started | 0% | 2 | 3 | 6 | 3 | Medium | On track | Exercise held; surge plan approved
A12 | R12 | Delayed review of test results leading to missed diagnosis | 10 | Mitigate | Deploy automated results-tracking dashboard and weekly audit sign-off | Clinical Director | Clinical Systems Lead | 2026-09-21 | 2026-12-11 | 9800 | In progress | 50% | 2 | 4 | 8 | 2 | Medium | On track | Unreviewed results >48h ≤ 5 per week
A13 | R13 | Medication prescribing error | 9 | Mitigate | Pharmacist-led prescribing audit and tuned decision-support alerts | Clinical Director | Lead Clinical Pharmacist | 2026-11-02 | 2027-01-15 | 5600 | Not started | 0% | 2 | 3 | 6 | 3 | Medium | On track | Medication incidents ≤ 20 per year
A14 | R16 | Failure to recognise deteriorating patient or sepsis at triage | 10 | Mitigate | Introduce NEWS2-based triage tool and sepsis simulation training for all patient-facing staff | Head of Nursing | Lead Nurse Practitioner | 2026-09-14 | 2026-11-20 | 4500 | In progress | 70% | 2 | 4 | 8 | 2 | Medium | On track | 100% staff trained; triage audit ≥ 95% compliant
A15 | R18 | Missed or late safeguarding referral | 10 | Mitigate | Safeguarding case audit, Level 3 refresher for all clinicians and quarterly case-review meetings | Safeguarding Lead | Safeguarding Lead | 2026-09-28 | 2026-12-04 | 3200 | In progress | 30% | 2 | 4 | 8 | 2 | Medium | On track | Level 3 compliance ≥ 95%
A16 | R19 | Clinical vacancies and burnout causing unsafe staffing | 12 | Mitigate | Recruit 2 salaried GPs and 1 ANP; launch retention and wellbeing programme | HR Manager | HR Manager / Practice Manager | 2026-09-01 | 2027-03-31 | 92000 | In progress | 25% | 3 | 3 | 9 | 3 | Medium | On track | Vacancy rate ≤ 8%; locum spend ≤ 12%
A17 | R20 | Mandatory training non-compliance | 6 | Mitigate | Automate training reminders and add manager escalation at 30 days overdue | HR Manager | HR Manager | 2026-09-01 | 2026-09-30 | 1500 | Complete | 100% | 2 | 2 | 4 | 2 | Low | Complete | Compliance ≥ 90% in all modules
A18 | R21 | Dependence on key individuals (single points of failure) | 9 | Mitigate | Document core procedures and cross-train deputies for key roles | Practice Manager | Practice Manager | 2026-11-02 | 2027-02-26 | 2500 | Not started | 0% | 2 | 3 | 6 | 3 | Medium | On track | Documented procedures for 100% of key roles
A19 | R22 | Adverse CQC inspection outcome or rating downgrade | 8 | Mitigate | Quarterly mock CQC inspections with action tracking | Quality & Compliance Lead | Quality & Compliance Lead | 2026-10-01 | 2026-12-18 | 6000 | In progress | 35% | 2 | 3 | 6 | 2 | Medium | On track | No major findings; actions closed in 30 days
A20 | R23 | Digital clinical safety and DSPT non-compliance | 9 | Mitigate | Appoint Clinical Safety Officer; formalise DCB0160 process; close DSPT evidence gaps | Quality & Compliance Lead | Quality & Compliance Lead | 2026-09-28 | 2026-11-27 | 4000 | In progress | 45% | 2 | 3 | 6 | 3 | Medium | On track | DSPT standards met; 100% new tools with safety case
A21 | R25 | Payroll or invoice fraud | 4 | Accept | Continue dual authorisation and annual internal audit of payment controls (BAU monitoring) | Finance Director | Finance Manager | 2026-04-01 | 2027-03-31 | - | Ongoing | 100% | 1 | 4 | 4 | 0 | Medium | BAU monitoring | Zero fraud losses; audit with no major findings
A22 | R26 | Failure of critical supplier (pathology or clinical waste) | 9 | Mitigate | Negotiate secondary pathology supplier and contract exit/step-in plan | Chief Executive | Chief Executive | 2026-11-02 | 2027-03-31 | 3500 | Not started | 0% | 2 | 3 | 6 | 3 | Medium | On track | Secondary agreement signed
A23 | R27 | Fire safety non-compliance | 10 | Mitigate | Fire door remediation and reinstate quarterly evacuation drills | Estates & Facilities Manager | Estates Officer | 2026-08-03 | 2026-10-09 | 22400 | In progress | 80% | 1 | 5 | 5 | 5 | Medium | Overdue | All fire doors certified; 4/4 drills per year
A24 | R28 | Legionella in water systems | 5 | Accept | Continue quarterly Legionella sampling and temperature monitoring (BAU monitoring) | Estates & Facilities Manager | Estates Officer | 2026-04-01 | 2027-03-31 | - | Ongoing | 100% | 1 | 5 | 5 | 0 | Medium | BAU monitoring | No positive samples; all logs complete
A25 | R29 | Violence and aggression towards staff | 8 | Mitigate | De-escalation training and reception CCTV and screen upgrade | Practice Manager | Practice Manager | 2026-10-12 | 2026-12-11 | 5200 | In progress | 25% | 3 | 2 | 6 | 2 | Medium | On track | Incidents ≤ 20 per year
A26 | R31 | Poor access: long waits and high DNA rates | 12 | Mitigate | Redesign access: online triage, DNA text reminders and capacity-demand review | Practice Manager | Practice Manager | 2026-10-01 | 2027-01-29 | 11000 | In progress | 20% | 3 | 3 | 9 | 3 | Medium | On track | DNA ≤ 6%; third-next-available ≤ 10 days
26 |  |  |  |  | Total / count |  |  |  |  | 323600
Assumption: costs are indicative estimates (first-year, incl. one-off and programme costs). Ongoing = business-as-usual control monitoring.

## KRI Data
Key Risk Indicators – Simulated 12 Months to 30 Sep 2026
Evidence used to support likelihood scoring. Status is a formula.
KRI ID | Linked risk | Indicator | Unit | Actual | Threshold | Direction | Status
K01 | R02 | Phishing simulation click rate | % | 11.8 | 5 | Lower is better | Breached
K02 | R02 | Staff accounts with MFA enabled | % | 58 | 100 | Higher is better | Breached
K03 | R03 | Critical patches applied within 14 days | % | 81 | 95 | Higher is better | Breached
K04 | R03 | Systems on unsupported operating systems | count | 4 | 0 | Lower is better | Breached
K05 | R01 | Quarterly backup restore tests passed (last 4) | % | 50 | 100 | Higher is better | Breached
K06 | R05 | Reported data incidents (12 months) | count | 23 | 15 | Lower is better | Breached
K07 | R05 | Of which misdirected email/letter | count | 14 | 8 | Lower is better | Breached
K08 | R05 | ICO-reportable breaches | count | 1 | 0 | Lower is better | Breached
K09 | R06 | SARs completed within one month | % | 88 | 95 | Higher is better | Breached
K10 | R06 | SARs received (12 months) | count | 148 | 150 | Lower is better | Within threshold
K11 | R09 | EPR unplanned downtime | hours | 9.5 | 8 | Lower is better | Breached
K12 | R12 | Test results unreviewed >48h (weekly average) | count | 17 | 5 | Lower is better | Breached
K13 | R13 | Medication incidents reported | count | 31 | 20 | Lower is better | Breached
K14 | R15 | Vaccine fridge temperature excursions | count | 3 | 0 | Lower is better | Breached
K15 | R18 | Level 3 safeguarding training compliance | % | 84 | 95 | Higher is better | Breached
K16 | R19 | Clinician vacancy rate | % | 17 | 8 | Lower is better | Breached
K17 | R19 | Locum spend as share of clinical pay | % | 21 | 12 | Lower is better | Breached
K18 | R20 | Mandatory training compliance | % | 82 | 90 | Higher is better | Breached
K19 | R27 | Fire drills completed vs planned | % | 50 | 100 | Higher is better | Breached
K20 | R29 | Violence and aggression incidents | count | 41 | 20 | Lower is better | Breached
K21 | R31 | DNA (did not attend) rate | % | 9.4 | 6 | Lower is better | Breached
K22 | R31 | Third next-available routine GP appointment | days | 17 | 10 | Lower is better | Breached
Simulated data for portfolio use. Thresholds are assumed internal tolerances.

## Risk Owners
Risk Owner Directory (fictional)
Role | Name | Reports to
Chief Executive | Neil Barker | Board / Partners
Clinical Director | Dr Helen Marsh | Chief Executive
Practice Manager | Tom Hughes | Chief Executive
Finance Director | James Whitfield | Chief Executive
Head of IT & Digital | Priya Nair | Practice Manager
Data Protection Officer | Aisha Rahman | Chief Executive (independent reporting line to Board)
Head of Nursing | Claire Donnelly | Clinical Director
Pharmacy Lead | Rachel Owen | Clinical Director
IPC Lead | Joanne Bell | Head of Nursing
Safeguarding Lead | Dr Samir Patel | Clinical Director
HR Manager | Sophie Walker | Practice Manager
Estates & Facilities Manager | Mark Ellison | Practice Manager
Quality & Compliance Lead | Grace Adeyemi | Chief Executive

## Risk Owners report
Risk Owner Report
Reporting date per Criteria sheet. All figures are live formulas except analyst commentary (as at 16 Oct 2026).
Headline metrics
Metric | Value
Risks on register | 31
Inherent Critical + High risks | 27
Residual Critical + High risks | 9
Risks outside appetite (residual) | 9
Outside-appetite risks with no treatment action | 0
Average inherent score | 13.5
Average residual score | 8.5
Treatment actions | 26
Actions open (not complete / BAU) | 23
Actions overdue | 1
Total treatment budget (£) | 323600
KRIs breached | 21
Report by risk owner
Risk owner (role) | Name | Risks owned | Avg inherent score | Avg residual score | Residual High/Critical | Outside appetite | Open actions | Overdue actions | Treatment budget (£) | Analyst commentary | Decision / support requested
Chief Executive | Neil Barker | 2 | 10.5 | 7.5 | 0 | 0 | 1 | 0 | 3500 | Supplier dependency on a single pathology provider is a latent risk; reputation risk is mitigated by communications readiness. | Authorise secondary supplier negotiation.
Clinical Director | Dr Helen Marsh | 2 | 15.5 | 9.5 | 1 | 1 | 2 | 0 | 15400 | Test-result review delays (17 per week) outside appetite; prescribing incidents above tolerance. | Mandate weekly results audit sign-off for all clinicians.
Practice Manager | Tom Hughes | 4 | 12.8 | 9.5 | 1 | 1 | 4 | 0 | 21700 | Patient access (DNA 9.4%) is outside appetite; violence and aggression incidents are high (41). Continuity depends on key-person cover. | Support access redesign and approve reception safety upgrade.
Finance Director | James Whitfield | 2 | 12 | 6.5 | 0 | 0 | 0 | 0 | - | Financial pressure is the main exposure; fraud controls are strong. | Confirm FY27 budget scenarios and insurance renewal.
Head of IT & Digital | Priya Nair | 5 | 16 | 10 | 3 | 3 | 6 | 0 | 107100 | Three of five risks sit outside appetite; ransomware, MFA and legacy systems drive the profile. Backup and MFA work is progressing; legacy remediation has not started. | Approve £38k legacy replacement and confirm cyber insurance renewal.
Data Protection Officer | Aisha Rahman | 4 | 13.8 | 7.8 | 0 | 0 | 3 | 0 | 11300 | All four privacy risks are within appetite but SAR timeliness (88%) and misdirected correspondence (14 incidents) trend adversely. | Endorse the audit-log review resource; keep AI scribe paused until DPIA sign-off.
Head of Nursing | Claire Donnelly | 1 | 15 | 10 | 1 | 1 | 1 | 0 | 4500 | Sepsis and deterioration recognition risk is outside appetite owing to impact; training programme is 70% complete. | Release staff time for simulation training.
Pharmacy Lead | Rachel Owen | 2 | 10.5 | 6 | 0 | 0 | 0 | 0 | - | Controlled drugs and cold chain remain controlled; three fridge excursions warrant continued monitoring. | None – continue monthly assurance.
IPC Lead | Joanne Bell | 1 | 12 | 6 | 0 | 0 | 0 | 0 | - | Single risk, strong controls; no outbreak or surgical-site cluster in the period. | None.
Safeguarding Lead | Dr Samir Patel | 1 | 15 | 10 | 1 | 1 | 1 | 0 | 3200 | Level 3 compliance 84% against 95% target; impact keeps residual risk outside appetite. | Protected time for clinician refresher training.
HR Manager | Sophie Walker | 2 | 16 | 9 | 1 | 1 | 1 | 0 | 93500 | Vacancy rate (17%) and locum reliance (21%) place workforce risk outside appetite; training compliance action completed. | Approve recruitment budget (£92k first-year).
Estates & Facilities Manager | Mark Ellison | 3 | 12.3 | 7.7 | 1 | 1 | 2 | 1 | 53400 | Fire safety remediation is overdue and sits outside appetite; resilience of the server room power remains a gap. | Release contractor capacity to close fire doors; approve UPS/generator budget.
Quality & Compliance Lead | Grace Adeyemi | 2 | 12 | 8.5 | 0 | 0 | 2 | 0 | 10000 | Governance risks within appetite; DSPT evidence gaps and absence of a Clinical Safety Officer need closing before year end. | Appoint Clinical Safety Officer by 27 Nov.
Total |  | 31 |  |  | 9 | 9 | 23 | 1 | 323600
Summary by risk category
Category | Risks | Avg residual score | Max residual score | Outside appetite
Cyber Security | 3 | 12 | 12 | 3
Data Protection | 4 | 7.8 | 9 | 0
Information Security | 1 | 6 | 6 | 0
Operational Resilience | 2 | 10 | 12 | 1
Business Continuity | 2 | 8.5 | 9 | 0
Clinical Safety | 3 | 9.7 | 10 | 2
Medicines Management | 2 | 6 | 6 | 0
Infection Prevention | 1 | 6 | 6 | 0
Safeguarding | 1 | 10 | 10 | 1
Workforce | 3 | 9 | 12 | 1
Regulatory Compliance | 2 | 8.5 | 9 | 0
Financial | 2 | 6.5 | 9 | 0
Supply Chain | 1 | 9 | 9 | 0
Estates & H&S | 3 | 7.7 | 10 | 1
Reputation | 1 | 6 | 6 | 0

## Risk Matrix
Risk Matrix – 5x5 Heat Maps
Counts are live formulas from the Risk Register; cell colours follow the fixed bands on the Criteria sheet (1–4 / 5–9 / 10–15 / 16–25).
Inherent risk – number of risks | [6 empty] | Rating summary
Likelihood ↓ / Impact → | Score | 1 | 2 | 3 | 4 | 5 | Rating | Inherent | Residual | Change
|  | Negligible | Minor | Moderate | Major | Severe | Critical | 7 | 0 | -7
5 Almost certain | 5 | 0 | 0 | 3 | 2 | 0 | High | 20 | 9 | -11
4 Likely | 4 | 0 | 0 | 2 | 4 | 1 | Medium | 4 | 21 | 17
3 Possible | 3 | 0 | 0 | 3 | 10 | 4 | Low | 0 | 1 | 1
2 Unlikely | 2 | 0 | 0 | 0 | 1 | 1 | Total | 31 | 31 | 0
1 Rare | 1 | 0 | 0 | 0 | 0 | 0
Residual risk – number of risks
Likelihood ↓ / Impact → | Score | 1 | 2 | 3 | 4 | 5
|  | Negligible | Minor | Moderate | Major | Severe
5 Almost certain | 5 | 0 | 0 | 0 | 0 | 0
4 Likely | 4 | 0 | 2 | 3 | 0 | 0
3 Possible | 3 | 0 | 2 | 7 | 2 | 0
2 Unlikely | 2 | 0 | 0 | 5 | 4 | 4
1 Rare | 1 | 0 | 0 | 0 | 1 | 1
Residual risk – risk IDs by cell
Likelihood ↓ / Impact → | Score | 1 | 2 | 3 | 4 | 5
|  | Negligible | Minor | Moderate | Major | Severe
5 Almost certain | 5
4 Likely | 4 |  | R05, R29 | R02, R19, R31
3 Possible | 3 |  | R06, R20 | R04, R11, R13, R21, R23, R24, R26 | R01, R03
2 Unlikely | 2 |  |  | R08, R14, R15, R17, R30 | R07, R09, R10, R22 | R12, R16, R18, R27
1 Rare | 1 |  |  |  | R25 | R28